## TEST_CASES
Tester Name | Roselle Mariano
Total # of Test Case | 31
Not Started
In Progress
Passed | 0
Failed | 0
Blocked | 0
Test ID | Module Name | Test Scenario | Pre-requisite | Environment Information | Test Data | Test Steps | Expected Results | Actual Results | Status | Comments
TC_001 | Implement Login | Username and password field should accept alpha-numeric characters only. | 1. Need to have Intellij 2. Running student-info-mgt-app. 3. Jars needed | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: esdi Password: Changeme0! | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.input the test data 5. click login | Login unsuccessful | Login successful | Not started | Bug
TC_002 | Implement Login | It should display “Username and password are required. “ when user did not enter either username or password. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: Password: Changeme0 | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.input the test data 5. click login | should display “Username and password are required" | Login successful and no display | Not started | Bug
TC_003 | Implement Login | It should display “No username found.“ when user entered an unregistered username. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: eshdi Password: Changeme0 | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.input the test data 5. click login | should display "No username found" | Login successful and no display | not started | Bug
TC_004 | Implement Login | It should display “Incorrect password. Please try again.“ if user entered an incorrect password. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: esdi Password: Changeme01 | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.input the test data 5. click login | should display "incorrect password" | Login successful and no display | Not started | Bug
TC_005 | Implement Login | When user has already entered correct credentials and user clicked the “Login“ button, user must be able to login to the system. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: esdi Password: Changeme0 | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.input the test data 5. click login | Login successful | Login successful | ok | None
TC_006 | Implement Login | If user did not enter both username and password and user clicked the “Login“ button, user must not be able to login to the system. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: Password: | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.input the test data 5. click login | Login unsuccessful | Login successful | On going | Bug
TC_007 | Implement Sign up | When user clicked the button “Sign up “ it should send the user to a new page to be able to fill up the forms. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | none | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button | proceeds to the create aacount page | proceeds to the create aacount page | ok | none
TC_008 | Implement Sign up | ID field should only accept numbers and it should display “Please enter valid input.“ whenever user tries to enter characters. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | ID: character | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data | it should display "Please enter valid input" | no display of "Please enter valid input" | Not Started | Bug
TC_009 | Implement Sign up | Username field should accept alpha-numeric characters only and it should display “Please enter valid input.“ whenever user tries to enter non alpha-numeric characters. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | ID:4 Username:Ros! Entity id: CT20-0123 | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "register now" | it should display "Please enter valid input" | Accepted the input | Not Started | Bug
TC_010 | Implement Sign up | Entity ID field should accept alpha-numeric characters only and it should display “Please enter valid input.“ whenever user tries to enter non alpha-numeric characters. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | ID:5 Username:Ros Entity id: CT20-0123 | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "register now" | it should display "Please enter valid input" | Accepted the input | Not Started | Bug
TC_011 | Implement Sign up | When user tries to click the “Sign up“ button without entering any credentials it should display “Please enter complete credentials/information.“. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | ID: Username: Entity id: | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "register now" | it should display "Please enter complete credentials" | no display of "Please enter complete credentials" | Not Started | Bug
TC_012 | Implement Forgot Password | Username field should accept alpha-numeric characters only and it should display “Please enter valid input.“ whenever user tries to enter non alpha-numeric characters. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: Ros! Childhood nickname: markian new password: mamamu | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | it should display "Please enter valid input" | accepts the invalid data, and does'nt display "please enter valid input" | Not Started | Bug
TC_013 | Implement Forgot Password | If user tries to enter unregistered username, it should display “Username not registered. Please sign up/create an account first.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: Rose Childhood nickname: markian new password: mamamu | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | it should display “Username not registered. Please sign up/create an account first.“ | does'nt display “Username not registered. Please sign up/create an account first.“ | Not Started | Bug
TC_014 | Implement Forgot Password | Childhood nickname should only accept “markian“ as an input. Changing password should not work if user tries to enter different nickname. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: esdi Childhood nickname: markians new password: mamamu | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | new password should not be saved in database | new password not saved in database | ok | None
TC_015 | Implement Forgot Password | New Password field should accept alpha-numeric characters only. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: esdi Childhood nickname: markian new password: mamamu# | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | it should display "Please enter valid input" | accepts the invalid data | Not Started | Bug
TC_016 | Implement Forgot Password | When “Save“ button is clicked, the new password set by the user should reflect in the database. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: esdi Childhood nickname: markian new password: mamamu | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | the new password should reflect on the database | new password reflects on the database | ok | None
TC_017 | Implement Forgot Password | When “Cancel“ button is clicked, it should redirect to the login page again. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username: esdi Childhood nickname: markian new password: mamsh | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "cancel" | redirect again back to login page | redirects again back to login page | ok
TC_018 | Implement Edit Function for User List | Username field should accept alpha-numeric characters only and it should display “Please enter valid input.“ whenever user tries to enter non alpha-numeric characters. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username:esdi current password: mamamu New pass: Changeme0! Confirm pass: Changeme0! | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | it should display “Please enter valid input.“ | accepts the invalid data and does not display “Please enter valid input.“ | Not started | Bug
TC_019 | Implement Edit Function for User List | Current Password field should only accept the registered password in the database. If user entered incorrect password, it should display “Password does not match with your current password.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username:esdi current password: Changeme New pass: mamamu Confirm pass: mamamu | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | it should display “Password does not match with your current password.“ | accepts the invalid data and does not display “Password does not match with your current password.“ | Not Started | Bug
TC_020 | Implement Edit Function for User List | New Password field should accept alpha-numeric characters only. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username:esdi current password: mamamu New pass: Changeme0! Confirm pass: Changeme0! | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | it should display “Please enter valid input.“ | accepts the invalid data and does not display “Please enter valid input.“ | Not Started | Bug
TC_021 | Implement Edit Function for User List | Confirm Password field should accept the same value the New Password field contains. If it does not match, it should display “Password does not match. Please try again.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username:esdi current password: Changeme0! New pass: tatayko Confirm pass: tataymu | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | it should display “Password does not match. Please try again.“ | accepts the invalid data and does not display “Password does not match. Please try again.“ | Not started | Bug
TC_022 | Implement Edit Function for User List | Save button should be disabled if user did not enter any information and it should display “Alll fields are important. Please enter valid input.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username:esdi current password: New pass: Confirm pass: | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "save" | it should display “Alll fields are important. Please enter valid input.“ | accepts null data and it does not display "All f ields are important. Please enter valid input" also saves as null in database | Not Started | Bug
TC_023 | Implement Edit Function for User List | When “Cancel“ button is clicked, it should redirect to the User List page again.. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | Username:esdi current password: mamamu New pass: tatayko Confirm pass: tataymu | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.click the sign up button 5. input the test data 6. click the button "cancel" | redirect again back to user list page | redirects again back to user list page | ok | None
TC_024 | Implement Add Function for Student List | Student ID fields should accept alpha-numeric characters only. If user tries to enter non alpha-numeric characters it should display “Invalid input.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | StudentID: CT21-009 LastName:Molina Firstname:Kimmy MiddleInitial: C Sex:Female Bday:01/04/2024 Religion: catholic email: kimmy@gmail.com contact no: 12345678999 address: batangas | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.Login 5.click student on left side 6.click the add student button 7. input the test data 8. click the button "add" | it should display “Invalid input.“ | accepts data and it does not display "Invalid input" | Not started | Bug
TC_025 | Implement Add Function for Student List | Last Name, First Name, and Middle Name fields should accept characters only. If user tries to enter non characters it should display “Invalid input.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | StudentID: CT21009 LastName:Mol! Firstname:Kimm@ MiddleInitial: # Sex:Female Bday:01/04/2024 Religion: catholic email: kimms@gmail.com contact no: 12345678998 address: batangas | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.Login 5.click student on left side 6.click the add student button 7. input the test data 8. click the button "add" | it should display “Invalid input.“ | accepts data and it does not display "Invalid input" | Not started | Bug
TC_026 | Implement Add Function for Student List | Birthday field should accept valid birthday only. It means that it should only accept inputs if the student is born at least 17 years ago. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | StudentID: CT21009 LastName:Mol! Firstname:Kimm@ MiddleInitial: # Sex:Female Bday:01/04/2024 Religion: catholic email: kimms@gmail.com contact no: 12345678998 address: batangas | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.Login 5.click student on left side 6.click the add student button 7. input the test data 8. click the button "add" | should not accept bday | accepts the bday | Not started | Bug
TC_027 | Implement Add Function for Student List | Religion field should accept accept characters only. If user tries to enter non characters it should display “Invalid input.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | StudentID: CT21008 LastName:Kim Firstname:Soohyun MiddleInitial: L Sex:Male Bday:01/04/2024 Religion: email: soohyun@gmail.com contact no: 45678912344 address:south korea | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.Login 5.click student on left side 6.click the add student button 7. input the test data 8. click the button "add" | should not accept null religion and display invalid input | accepts null input and does not dsiplay "Invalid input" | Not started | Bug
TC_028 | Implement Add Function for Student List | Email field should not accept any input without “@gmail.com“. If user tries to input different value, it should display “Invalid email address.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | StudentID: CT21007 LastName:Baek Firstname:Hyunwoo MiddleInitial: L Sex:Male Bday:01/04/2024 Religion: Catholic email: hyunwoo contact no: 12345607894 address:south korea | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.Login 5.click student on left side 6.click the add student button 7. input the test data 8. click the button "add" | should not accept any input without “@gmail.com“ and it should display “Invalid email address.“ | accepts data and it does not display “Invalid email address.“ | Not started | Bug
TC_029 | Implement Add Function for Student List | Contact Number field should only accept exact 11 numbers. It should display “Invalid input“ if the input of user is more than or less than 11. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | StudentID: CT21007 LastName:Baek Firstname:Hyunwoo MiddleInitial: L Sex:Male Bday:01/04/2024 Religion: Catholic email: hyunwoo contact no: 123456 address:south korea | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.Login 5.click student on left side 6.click the add student button 7. input the test data 8. click the button "add" | It should not accept data and display “Invalid input“ if the input of user is more than or less than 11. | accepts data and does not display “Invalid input“ if the input of user is more or less than 11 | Not started | None
TC_030 | Implement Add Function for Student List | Address fields should accept alpha-numeric characters only. If user tries to enter non alpha-numeric characters it should display “Invalid input.“ | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | StudentID: CT21007 LastName:Baek Firstname:Hyunwoo MiddleInitial: L Sex:Male Bday:01/04/2024 Religion: Catholic email: hyunwoo contact no: 123456789123 address:south korea! | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.Login 5.click student on left side 6.click the add student button 7. input the test data 8. click the button "add" | should accept alpha-numeric characters only also it should display “Invalid input.“ | accept non alpha-numeric characters also it does not display “Invalid input.“ | Not started | Bug
TC_031 | Implement Add Function for Student List | If “Add“ or “Cancel“ button is clicked, it should redirect the user to the Student List/Table only. | 1. Need to have Intellij 2. Running student-info-mgt-app | 1. OS: Windows/Linux/Mac 2. System: Laptop/Desktop | StudentID: CT21007 LastName:Baek Firstname:Hyunwoo MiddleInitial: L Sex:Male Bday:01/04/2024 Religion: Catholic email: hyunwoo contact no: 123456789123 address:south korea! | 1.open the student-info-mtg-app 2.fixed the project structure 3. run the main 4.Login 5.click student on left side 6.click the add student button 7. input the test data 8. click the button "add" 9.input the test data 10. click the button "cancel" | it should redirect the user to the Student List/Table only. | redirects to student list table when cancel button is clicked. Automatically exits when adding student | inprogress | Automatically exits when adding student